## Bug Sheet
Bug ID | Title / Summary | Module / Feature | Environment | Browser / Device | Build Version | Severity | Priority | Status | Reporter | Assigned To | Date Reported | Steps to Reproduce | Expected Result | Actual Result | Attachments / Evidence | Comments | Developer Comment
SD-001 | Login validation reports only missing username when both fields are empty | Authentication / Login | TBD | TBD | TBD | Medium | High | New | TBD | TBD | 2026-10-25 | 1. Open the login page. 2. Leave Username and Password empty. 3. Click Login. 4. Observe the validation message. (standard_user) | The application should clearly communicate that both username and password are required. | The application communicates only that the username is missing. | TBD | Credentials used: standard_user / secret_sauce. Confirm exact validation wording. | TBD
SD-002 | Product catalog displays unexpected product description and name | Inventory / Product Catalog | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as standard_user. 2. Open the inventory page. 3. Inspect Sauce Labs Backpack and Test.allTheThings() T-Shirt (Red). | Each product should display its correct name and description. | Sauce Labs Backpack displays 'carry.allTheThings()' unexpectedly in its description; Test.allTheThings() T-Shirt (Red) displays an unexpected name. | TBD | Credentials used: standard_user / secret_sauce. | TBD
SD-003 | Product quantity cannot be increased from the inventory or product page | Inventory / Product Details / Cart | TBD | TBD | TBD | Medium | Medium | New | TBD | TBD | 2026-10-25 | 1. Log in as standard_user. 2. Open a product. 3. Attempt to select a quantity greater than one before adding it to the cart. | Where multi-quantity purchasing is supported, the user should be able to specify the desired quantity. | No control is available to select more than one unit of a product. | TBD | Confirm whether quantity selection is a product requirement; this may be a requirement gap rather than a defect. | TBD
SD-004 | Browser navigation allows access to checkout confirmation after payment completion | Checkout / Navigation | TBD | TBD | TBD | Medium | Medium | New | TBD | TBD | 2026-10-25 | 1. Log in as standard_user. 2. Complete checkout. 3. Use the browser Back button to return to the previous page. 4. Use Forward to return to the confirmation page. | Post-checkout navigation should preserve a consistent order state and should not allow unintended duplicate or inconsistent transactions. | The user can navigate backward after payment and forward to the confirmation page again. | TBD | Clarify whether the concern is duplicate submission, stale confirmation, or browser-history behavior. | TBD
SD-005 | Checkout completes without requesting payment details | Checkout / Order Processing | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as standard_user. 2. Add a product to the cart. 3. Proceed through checkout. 4. Observe whether payment details are requested before confirmation. | The checkout flow should collect or explicitly handle all required order and payment information before confirming an order. | Checkout confirmation is displayed and shipping is shown as ready without requesting payment details. | TBD | Validate against the application's intended checkout requirements; demo apps may intentionally omit payment fields. | TBD
SD-006 | User can complete checkout with an empty cart | Cart / Checkout | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in. 2. Ensure the cart is empty. 3. Navigate through checkout using available controls or browser navigation. 4. Observe whether checkout can be completed. | Checkout should be blocked when the cart contains no items. | The user can proceed through the end-to-end checkout flow without an item in the cart. | TBD | Observation was repeated in the original notes; recorded once. | TBD
SD-007 | Cart items persist across logout and login with a different account | Cart / Session Management | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in with account A and add products to the cart. 2. Log out. 3. Log in with a different account. 4. Inspect the cart. | A user's cart should be isolated according to the application's intended account/session behavior; one user's items should not unexpectedly appear for another user. | Cart items remain after logout and are visible after logging in with a different account. | TBD | Confirm expected cart persistence behavior for this application. | TBD
SD-008 | Inventory list displays identical product images for all products | Inventory / Product Images | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Open the inventory page. 3. Compare the images shown on multiple product cards. 4. Open product details and compare images. | Each product card and its detail page should display the correct image for that product. | All products display the same image on the inventory page, while the product detail pages show different images. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-009 | Browser Forward restores inventory and allows checkout flow after returning to login | Authentication / Browser Navigation | TBD | TBD | TBD | Medium | Medium | New | TBD | TBD | 2026-10-25 | 1. Log in and reach the inventory page. 2. Navigate back to the login page using browser navigation. 3. Click Forward. 4. Attempt to continue shopping and complete checkout. | Protected pages should enforce appropriate authentication and maintain a consistent session state when navigating through browser history. | The inventory page can be restored with Forward and the user can continue the purchase flow. | TBD | Clarify whether the session is expected to remain active or be invalidated when returning to login. | TBD
SD-010 | Inventory sorting or filtering controls do not work | Inventory / Sorting and Filtering | TBD | TBD | TBD | Medium | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Open the inventory page. 3. Attempt to sort or filter the product list using the available controls. | Available sort and filter controls should reorder or narrow the product list according to the selected option. | The user is unable to sort or filter the inventory list. | TBD | Credentials used: problem_user / secret_sauce. Record the selected sort/filter option during retest. | TBD
SD-011 | Selecting lazy-load dynamic catalog causes duplicate inventory items | Inventory / Dynamic Catalog Loading | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Select or trigger lazy-load dynamic catalog behavior. 3. Scroll through the inventory list. 4. Check for repeated products. | Each catalog item should appear once unless duplicates are intentionally part of the data. | Inventory items are duplicated when lazy-load dynamic catalog is selected. | TBD | Credentials used: problem_user / secret_sauce. Clarify how lazy-load mode is selected. | TBD
SD-012 | Inventory page cannot add more than two items to cart | Inventory / Cart Actions | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. On the inventory page, add products to the cart. 3. Attempt to add more than two products. 4. Open a product detail page and try adding from there. | The user should be able to add all eligible products to the cart from the inventory page. | The inventory page does not allow adding more than two items, although adding from product details is possible. | TBD | Credentials used: problem_user / secret_sauce. Clarify whether 'two items' means two distinct products or quantity. | TBD
SD-013 | Remove action is unavailable or non-functional on inventory product cards | Inventory / Cart Actions | TBD | TBD | TBD | Medium | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Add a product from the inventory list. 3. Attempt to remove the selected product using the inventory-page control. | The user should be able to remove a previously added product directly from the inventory page. | The user cannot remove selected items from the inventory list. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-014 | Sauce Labs Fleece Jacket detail page displays ITEM NOT FOUND despite allowing add to cart | Product Details / Cart | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Select Sauce Labs Fleece Jacket from inventory. 3. Inspect the detail page. 4. Attempt to add the product to the cart. | The selected product detail page should display the correct product information and allow valid cart actions. | The detail page displays ITEM NOT FOUND, but the product can still be added to the cart. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-015 | Selecting Sauce Labs Onesie opens details for Test.allTheThings() T-Shirt (Red) | Product Details / Product Mapping | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Select Sauce Labs Onesie from inventory. 3. Compare the detail-page name and information with the selected product. | The detail page should show Sauce Labs Onesie and its corresponding information. | The detail page displays Test.allTheThings() T-Shirt (Red). | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-016 | Selecting Test.allTheThings() T-Shirt (Red) opens Sauce Labs Backpack details | Product Details / Product Mapping | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Select Test.allTheThings() T-Shirt (Red) from inventory. 3. Inspect the product detail page. | The detail page should display Test.allTheThings() T-Shirt (Red) and its correct information. | The detail page displays Sauce Labs Backpack. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-017 | Selecting Sauce Labs Backpack opens Fleece Jacket details and prevents adding to cart | Product Details / Product Mapping / Cart | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Select Sauce Labs Backpack from inventory. 3. Inspect the detail page. 4. Attempt to add the selected product to the cart. | The detail page should show Sauce Labs Backpack and allow the product to be added to the cart. | The detail page displays Sauce Labs Fleece Jacket and the item cannot be added to the cart from the detail page. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-018 | Selecting Sauce Labs Bike Light opens Sauce Labs Bolt T-Shirt details and prevents adding to cart | Product Details / Product Mapping / Cart | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Select Sauce Labs Bike Light from inventory. 3. Inspect the detail page. 4. Attempt to add the selected product to the cart. | The detail page should show Sauce Labs Bike Light and allow the product to be added to the cart. | The detail page displays Sauce Labs Bolt T-Shirt and the item cannot be added from the detail page. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-019 | Checkout continues without a last name | Checkout / Customer Information Validation | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Add a product to the cart. 2. Proceed to checkout. 3. Leave Last Name empty. 4. Complete the remaining available fields. 5. Click Continue. | Checkout should validate all required customer information and display a clear error when Last Name is missing. | The user can proceed to the checkout overview page without entering a last name. | TBD | Validate whether Last Name is a mandatory field in the requirements. | TBD
SD-020 | Cart item count does not match the products displayed in the cart | Cart / Cart Count Integrity | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Add products including Sauce Labs Fleece Jacket that displays ITEM NOT FOUND. 3. Open the cart. 4. Compare the cart indicator with the visible cart items. | The cart indicator should match the number of items represented in the cart, according to the application's counting rules. | The cart indicator shows 4 while the cart displays 3 items. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-021 | Last Name input populates the First Name field on checkout | Checkout / Customer Information Form | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Add a product to the cart. 3. Open checkout. 4. Enter text in the Last Name field. 5. Observe which field receives the text. | Text entered in Last Name should remain in the Last Name field without changing First Name. | Text entered in Last Name appears in the First Name field. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-022 | Remove button does not remove Fleece Jacket from cart | Cart / Remove Item | TBD | TBD | TBD | Medium | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Open Sauce Labs Fleece Jacket details. 3. Add the item to the cart. 4. Open the cart and click Remove. | The selected item should be removed from the cart and the cart indicator should update. | Remove is non-functional; the item can only be cleared by clearing the whole cart and refreshing the page. | TBD | Credentials used: problem_user / secret_sauce. | TBD
SD-023 | Sauce Labs Fleece Jacket cannot be added from product details | Product Details / Cart | TBD | TBD | TBD | High | High | New | TBD | TBD | 2026-10-25 | 1. Log in as problem_user. 2. Open Sauce Labs Fleece Jacket details. 3. Click Add to Cart. | The product should be added to the cart and reflected in the cart indicator. | The user is unable to add Sauce Labs Fleece Jacket from the details page. | TBD | Credentials used: problem_user / secret_sauce. Related but distinct from SD-014: this report focuses on add-to-cart failure. | TBD
SD-024 | Remove button does not remove Sauce Labs Bike Light from cart | Cart / Remove Item | TBD | TBD | TBD | Medium | High | New | TBD | TBD | 2026-10-25 | 1. Log in as error_user. 2. Open Sauce Labs Bike Light details. 3. Add the item to the cart. 4. Open the cart and click Remove. | The selected item should be removed from the cart and the cart indicator should update. | Remove is non-functional until the cart is cleared and the page is refreshed. | TBD | Credentials used: error_user / secret_sauce. | TBD
SD-025 | Remove button becomes non-functional for Sauce Labs Onesie | Cart / Remove Item | TBD | TBD | TBD | Medium | High | New | TBD | TBD | 2026-10-25 | 1. Log in as error_user. 2. Open Sauce Labs Onesie details. 3. Add the item to the cart. 4. Open the cart and click Remove. | The selected item should be removed from the cart. | The Remove button becomes non-functional and the item cannot be removed through the normal action. | TBD | Credentials used: error_user / secret_sauce. | TBD
SD-026 | Cart button is misaligned and distorts the page layout | UI / Cart Navigation | TBD | TBD | TBD | Low | Medium | New | TBD | TBD | 2026-10-25 | 1. Log in as visual_user. 2. Inspect the cart button on the page at the affected viewport. 3. Observe alignment and surrounding layout. | The cart button should be aligned consistently without overlapping or distorting other page elements. | The cart button is incorrectly displayed or aligned and makes the page appear distorted. | TBD | Credentials used: visual_user / secret_sauce. Capture viewport dimensions and screenshot. | TBD
SD-027 | Checkout button appears at the top-right instead of the bottom-right of the cart page | UI / Cart Page Layout | TBD | TBD | TBD | Low | Medium | New | TBD | TBD | 2026-10-25 | 1. Log in as visual_user. 2. Open the cart page. 3. Inspect the Checkout button position and page layout. | The Checkout button should be positioned according to the intended cart-page layout, at the expected bottom-right location. | The Checkout button appears at the top-right and distorts the page layout. | TBD | Credentials used: visual_user / secret_sauce. Confirm intended layout against design/reference. | TBD
SD-028 | Hamburger menu is visibly slanted | UI / Navigation Menu | TBD | TBD | TBD | Low | Low | New | TBD | TBD | 2026-10-25 | 1. Log in as visual_user. 2. Inspect the hamburger menu icon. 3. Observe the alignment of its lines. | The hamburger menu icon should be correctly aligned and rendered without visual distortion. | The hamburger menu appears slanted. | TBD | Credentials used: visual_user / secret_sauce. | TBD
SD-029 | Noticeable response delay during login and navigation | Performance / Authentication / Navigation | TBD | TBD | TBD | Medium | Medium | New | TBD | TBD | 2026-10-25 | 1. Log in as performance_glitch_user. 2. Observe the time taken for login to complete. 3. Open a product detail page and return to inventory. 4. Observe delays. | Login and page navigation should complete within the agreed performance targets with clear loading feedback where needed. | Actions such as login and returning from product details to inventory pause for several seconds before the next screen appears. | TBD | Credentials used: performance_glitch_user / secret_sauce. Capture measured timings, browser console, and network details. | TBD